## Sheet1
Week |  |  | Risks
40 | 2020-09-28 | first design
41 | 2020-10-05 | Simulation of various designs |  | Missing parts | Amount | Budget
42 | 2020-10-12 | Simulation of various designs |  | controller | 1
43 | 2020-10-19 | BMS and baterry package building; Order missing components |  | parts for inductance |  | 60
44 | 2020-10-26 | build and calculate the inductance; Case Design |  | Multimeter for MC | 4 | 40
45 | 2020-11-02 | building converter |  | Capacitor | 1 | 20
46 | 2020-11-09 | Controller programming sensors |  | Circuit board | 1 | 30
47 | 2020-11-16 | Testing Components bevor assembling |  | BMS | 2 | 340
48 | 2020-11-23 | Assamble complete charger with case |  | OP amps | 2 | 15
49 | 2020-11-30 | Testing charger to accurate values and efficency |  | Connectors | 2 | 80
50 | 2020-12-07 |  |  | LED for charging signal | 4 (2xr, 2xg) | 135
51 | 2020-12-14 |  |  | battery capacity |  | 28
52 | 2020-12-21 |  |  | testing board | 2 | 60
808